## Overview
Agentic AI Offering — Project Plan & Execution Pack
Complex Project Manager working pack • 8 phases • RACI • Risks • Checklists • Templates
Purpose | Provide a single source of truth for planning, executing and governing an Agentic AI offering — from use-case discovery through scale-up. Designed to be cloned per engagement.
Workbook contents | 1) Project Plan 2) Milestones & Gates 3) RACI Matrix 4) Execution Checklist 5) Risk Register 6) Status Report template 7) Decision Log template
How to use | • Tailor durations and owners in 'Project Plan' • Run a stage-gate review at every milestone in 'Milestones & Gates' • Re-score risks weekly • Refresh status with the template before every steerco.
Assumed team archetypes | Sponsor • Product Owner • Project Manager • Solution Architect • AI/ML Engineer • Data Engineer • MLOps/Platform • Security & Risk • UX / Designer • Business SME • QA / Eval Lead • Change & Adoption Lead
Default cadence | Daily stand-up (build phases) • Weekly status to PMO • Bi-weekly steerco • Stage-gate review at each phase exit
The 8 phases at a glance
# | Phase | Primary outcome | Duration (wks) | Lead role | Exit gate
1 | Discovery & Use-Case Definition | Prioritised use case + value case | 3 | Product Owner | Use-case charter signed-off
2 | Strategy, Architecture & Design | Target agent architecture & tech stack | 3 | Solution Architect | Architecture review board approval
3 | Data Readiness & Infra Setup | Data, KB, env, security ready | 4 | Data Engineer | Data & infra readiness review
4 | Build & Develop Agent | Working MVP agent in dev | 5 | AI/ML Engineer | MVP demo + code review
5 | Test, Eval & Red-Team | Eval scorecard meets thresholds | 3 | QA / Eval Lead | Quality & safety gate passed
6 | Pilot / UAT | Business sign-off from pilot users | 3 | Business SME | Go / No-Go for production
7 | Deployment & Change Mgmt | Live agent + trained users | 2 | Project Manager | Production go-live
8 | Monitor, Optimise & Scale | Steady-state ops + scale plan | Ongoing | MLOps / Platform | Quarterly governance review

## Project Plan
Project Plan — Phases, tasks, owners, durations
Update Start Week / Duration to recalc End Week and view dependencies. Status uses a drop-down.
Phase | Task ID | Task / Activity | Description / Notes | Owner role | Duration (days) | Start week | End week | Dependencies | Key deliverable | Status
1. Discovery & Use-Case Definition | 1.1 | Sponsor & stakeholder alignment | Identify exec sponsor; align on ambition, scope, budget, success criteria. | Project Manager | 5 | 1 | 1 | — | Stakeholder map + ambition statement | Not started
1. Discovery & Use-Case Definition | 1.2 | Use-case long-list & prioritisation | Workshop to generate candidate use cases; score on value, feasibility, risk, data readiness. | Product Owner | 7 | 1 | 2 | 1.1 | Scored use-case backlog | Not started
1. Discovery & Use-Case Definition | 1.3 | Agent-vs-automation triage | Decide whether selected use case truly needs agentic capability (planning, tool use, autonomy) or simpler automation. | Solution Architect | 3 | 2 | 2 | 1.2 | Agentic suitability memo | Not started
1. Discovery & Use-Case Definition | 1.4 | Value case & target KPIs | Quantify benefit (time saved, $ impact, quality lift), define leading & lagging KPIs. | Product Owner | 5 | 2 | 2 | 1.2 | Value case & KPI tree | Not started
1. Discovery & Use-Case Definition | 1.5 | Use-case charter sign-off | Compile charter (problem, users, scope, KPIs, risks, team) for sponsor approval. | Project Manager | 3 | 3 | 3 | 1.3,1.4 | Signed use-case charter | Not started
2. Strategy, Architecture & Design | 2.1 | Agent pattern selection | Single agent vs orchestrator-with-sub-agents vs swarm; reasoning + planning loop design. | Solution Architect | 4 | 4 | 4 | 1.5 | Agent pattern decision record | Not started
2. Strategy, Architecture & Design | 2.2 | LLM / model selection | Evaluate candidate models on capability, latency, cost, hosting, data residency. | AI/ML Engineer | 4 | 4 | 4 | 2.1 | Model selection matrix | Not started
2. Strategy, Architecture & Design | 2.3 | Tools, MCP & integrations map | Catalogue tools the agent needs (APIs, MCP servers, RPA, search, RAG); identify build vs buy. | Solution Architect | 5 | 4 | 4 | 2.1 | Tool & integration inventory | Not started
2. Strategy, Architecture & Design | 2.4 | Memory, context & RAG design | Short-term context strategy, long-term memory store, RAG pipeline, chunking & embedding model. | AI/ML Engineer | 5 | 5 | 5 | 2.2,2.3 | Memory & retrieval design doc | Not started
2. Strategy, Architecture & Design | 2.5 | Guardrails, safety & HITL | Policy guardrails, PII redaction, tool allow-lists, human-in-the-loop checkpoints, escalation paths. | Security & Risk | 5 | 5 | 5 | 2.1 | Guardrail & HITL policy | Not started
2. Strategy, Architecture & Design | 2.6 | Target architecture & tech stack | End-to-end reference architecture (UI, orchestration, models, tools, data, observability, security). | Solution Architect | 5 | 6 | 6 | 2.4,2.5 | Solution architecture doc | Not started
2. Strategy, Architecture & Design | 2.7 | Architecture review board sign-off | Present to ARB for approval before any build commits. | Solution Architect | 2 | 6 | 6 | 2.6 | ARB approval | Not started
3. Data Readiness & Infra Setup | 3.1 | Data inventory & lineage | List source systems, ownership, sensitivity, refresh cadence; capture lineage where missing. | Data Engineer | 7 | 7 | 8 | 2.6 | Data inventory & lineage map | Not started
3. Data Readiness & Infra Setup | 3.2 | Data quality & access remediation | Profile data; fix gaps; secure access agreements (DPAs) with system owners. | Data Engineer | 10 | 7 | 8 | 3.1 | Data quality report + signed DPAs | Not started
3. Data Readiness & Infra Setup | 3.3 | Knowledge base & vector store build | Ingest docs, chunk, embed, index; tune retrieval; baseline retrieval quality. | AI/ML Engineer | 10 | 8 | 9 | 3.2 | Production-grade KB | Not started
3. Data Readiness & Infra Setup | 3.4 | Environments (dev / test / prod) | Provision cloud, networking, IAM, secrets, CI/CD; cost guardrails. | MLOps / Platform | 10 | 8 | 9 | 2.6 | Three working environments | Not started
3. Data Readiness & Infra Setup | 3.5 | Observability & telemetry stack | Tracing across agent loop, prompt/response logging, token & cost metrics, eval pipelines hook. | MLOps / Platform | 7 | 9 | 10 | 3.4 | Observability dashboard | Not started
3. Data Readiness & Infra Setup | 3.6 | Data & infra readiness gate | Joint review by Architect + Security + MLOps; sign-off to start build. | Project Manager | 3 | 10 | 10 | 3.3,3.5 | Readiness sign-off | Not started
4. Build & Develop Agent | 4.1 | Prompt & policy authoring | System prompt, role/persona, planning prompts, refusal & escalation policies. | AI/ML Engineer | 7 | 11 | 12 | 3.6 | Versioned prompt library | Not started
4. Build & Develop Agent | 4.2 | Tool development & MCP wiring | Build / integrate each tool the agent needs; standardise schemas; error handling. | AI/ML Engineer | 14 | 11 | 13 | 3.6 | Working tools / MCP servers | Not started
4. Build & Develop Agent | 4.3 | Orchestration & sub-agents | Implement planner, executor loop, sub-agent routing, retries, max-turns guard. | AI/ML Engineer | 14 | 12 | 14 | 4.1,4.2 | Agent orchestration layer | Not started
4. Build & Develop Agent | 4.4 | Front-end / channel integration | Chat UI, Teams/Slack/email channel, or embedded experience. | AI/ML Engineer | 10 | 13 | 14 | 4.3 | User-facing channel | Not started
4. Build & Develop Agent | 4.5 | Eval harness implementation | Build eval datasets (happy path, edge, adversarial); wire to CI for every change. | QA / Eval Lead | 10 | 13 | 14 | 4.3 | Automated eval harness | Not started
4. Build & Develop Agent | 4.6 | MVP demo & code review | Internal demo, code review, security review, decision to enter test phase. | Project Manager | 3 | 15 | 15 | 4.4,4.5 | Demo + review minutes | Not started
5. Test, Eval & Red-Team | 5.1 | Functional & regression testing | Run eval harness on full dataset; track quality, latency, cost per request. | QA / Eval Lead | 7 | 16 | 17 | 4.6 | Eval scorecard v1 | Not started
5. Test, Eval & Red-Team | 5.2 | Safety & adversarial red-team | Prompt injection, jailbreak, data exfiltration, tool misuse, role-confusion scenarios. | Security & Risk | 10 | 16 | 17 | 4.6 | Red-team report | Not started
5. Test, Eval & Red-Team | 5.3 | Bias, hallucination & accuracy review | Sample-based human review of agent outputs against ground truth. | QA / Eval Lead | 7 | 17 | 18 | 5.1 | Human review log | Not started
5. Test, Eval & Red-Team | 5.4 | Performance & cost tuning | Caching, prompt compression, model routing, parallelisation to hit SLAs. | AI/ML Engineer | 7 | 17 | 18 | 5.1 | Tuned MVP | Not started
5. Test, Eval & Red-Team | 5.5 | Quality & safety gate | Cross-functional review against acceptance thresholds; decide UAT entry. | Project Manager | 2 | 18 | 18 | 5.2,5.3,5.4 | Gate decision record | Not started
6. Pilot / UAT | 6.1 | Pilot user cohort onboarding | Select 10-30 pilot users; train; capture baseline KPIs. | Business SME | 5 | 19 | 19 | 5.5 | Pilot onboarding pack | Not started
6. Pilot / UAT | 6.2 | Pilot run & feedback loop | Run pilot with daily triage of issues, weekly prompt/policy iteration. | Product Owner | 14 | 19 | 21 | 6.1 | Pilot results dashboard | Not started
6. Pilot / UAT | 6.3 | UAT scenarios & sign-off | Business-led structured UAT against acceptance criteria. | Business SME | 7 | 20 | 21 | 6.2 | UAT sign-off | Not started
6. Pilot / UAT | 6.4 | Go / No-Go decision | Steerco decision based on pilot KPIs, UAT, risks, costs. | Sponsor | 2 | 21 | 21 | 6.3 | Go / No-Go record | Not started
7. Deployment & Change Mgmt | 7.1 | Production cutover plan | Cutover runbook, rollback plan, comms freeze, on-call roster. | MLOps / Platform | 5 | 22 | 22 | 6.4 | Cutover runbook | Not started
7. Deployment & Change Mgmt | 7.2 | Training & enablement | Role-based training, quick-reference guides, super-user network. | Change & Adoption Lead | 7 | 22 | 23 | 6.4 | Training collateral + sessions | Not started
7. Deployment & Change Mgmt | 7.3 | Communications & launch | Launch comms, leadership endorsement, FAQ, support channel. | Change & Adoption Lead | 5 | 23 | 23 | 7.2 | Launch comms pack | Not started
7. Deployment & Change Mgmt | 7.4 | Production go-live | Phased rollout, hypercare team stood up. | Project Manager | 3 | 23 | 23 | 7.1,7.3 | Live agent | Not started
8. Monitor, Optimise & Scale | 8.1 | Hypercare & incident triage | Daily monitoring, rapid fixes for first 2-4 weeks post go-live. | MLOps / Platform | 14 | 24 | 26 | 7.4 | Hypercare log | Not started
8. Monitor, Optimise & Scale | 8.2 | Continuous eval & drift monitoring | Automated eval on each release; track quality / cost / latency drift. | QA / Eval Lead | 30 | 24 | 29 | 7.4 | Drift & eval dashboard | Not started
8. Monitor, Optimise & Scale | 8.3 | Cost & performance optimisation | Model routing, caching, batching, prompt-cost reviews. | AI/ML Engineer | 30 | 25 | 30 | 8.2 | Cost optimisation report | Not started
8. Monitor, Optimise & Scale | 8.4 | Benefits realisation tracking | Measure realised KPIs vs business case; report monthly. | Product Owner | 30 | 25 | 30 | 7.4 | Benefits tracker | Not started
8. Monitor, Optimise & Scale | 8.5 | Governance cadence | Quarterly AI governance review (risk, compliance, model updates). | Security & Risk | 5 | 26 | 26 | 7.4 | Quarterly review pack | Not started
8. Monitor, Optimise & Scale | 8.6 | Scale to next use cases | Re-use platform, prompts, tools to onboard the next use case from backlog. | Product Owner | 30 | 26 | 31 | 1.2,8.4 | Scale-up plan | Not started

## Milestones & Gates
Milestones & Stage Gates
Each phase exits through a gate. No gate, no spend on the next phase.
Gate # | Milestone / Gate | Target week | Entry criteria | Exit criteria | Decision owner
G1 | Use-case charter signed-off | 3 | Stakeholders aligned; backlog scored | Signed charter, KPIs, named team | Sponsor
G2 | Architecture Review Board approval | 6 | Pattern, model, tools, guardrails drafted | Architecture approved; security cleared | ARB chair
G3 | Data & infra readiness | 10 | Data inventory + envs provisioned | Data quality, KB, observability in place | Solution Architect
G4 | MVP demo & code review | 15 | All Phase-4 tasks complete | Demoable agent, code review passed | Project Manager
G5 | Quality & safety gate | 18 | Eval & red-team complete | Eval ≥ thresholds; no Sev-1 safety findings | Security & Risk + QA Lead
G6 | Go / No-Go for production | 21 | Pilot KPIs reported; UAT done | KPIs meet target; sponsor sign-off | Sponsor
G7 | Production go-live | 23 | Cutover plan signed; training done | Agent live; hypercare active | Project Manager
G8 | Quarterly governance review | Q+1 | 90 days live | No open Sev-1/2; benefits on-track | AI Governance Committee

## RACI Matrix
RACI Matrix
R = Responsible (does the work) • A = Accountable (single owner) • C = Consulted • I = Informed
Activity | Sponsor | Product Owner | Project Manager | Solution Architect | AI/ML Engineer | Data Engineer | MLOps / Platform | Security & Risk | UX / Designer | Business SME | QA / Eval Lead | Change & Adoption | Legal / Compliance
Sponsor & stakeholder alignment | A | C | R | I | I | I | I | I | I | C | I | C | I
Use-case prioritisation | A | R | C | C | C | C | I | C | C | C | I | I | I
Agent suitability assessment | I | C | I | A | R | C | C | C | I | C | C | I | I
Value case & KPI definition | A | R | C | C | C | C | I | C | I | C | I | C | I
Agent pattern & architecture | I | C | I | A | R | C | C | C | C | I | C | I | I
LLM / model selection | I | C | I | C | A | C | C | C | I | I | C | I | C
Tools, MCP & integrations design | I | C | I | A | R | C | C | C | I | C | C | I | I
Memory & RAG design | I | C | I | C | A | R | C | C | I | I | C | I | I
Guardrails, safety & HITL | I | C | C | C | C | I | I | A | I | C | R | I | C
Data inventory & access | I | C | I | C | C | A | C | C | I | C | I | I | C
Knowledge base & vector store | I | C | I | C | R | A | C | C | I | C | I | I | I
Environments & CI/CD | I | I | I | C | C | C | A | C | I | I | C | I | I
Observability & telemetry | I | I | I | C | C | C | A | C | I | I | R | I | I
Prompt & policy authoring | I | C | I | C | A | I | I | C | I | C | R | I | C
Agent orchestration build | I | C | I | C | A | C | C | I | I | I | R | I | I
Front-end / channel integration | I | C | I | C | R | I | C | I | A | C | C | C | I
Eval harness & test datasets | I | C | I | C | C | C | C | C | I | C | A | I | I
Red-team & safety testing | I | C | I | C | C | I | C | A | I | I | R | I | C
Pilot run & feedback | I | A | R | C | C | C | C | C | C | R | C | C | I
UAT & business sign-off | A | C | C | I | I | I | I | C | C | R | C | C | I
Production cutover | I | C | R | C | C | C | A | C | I | I | C | C | I
Training & enablement | I | C | C | I | I | I | I | I | C | C | I | A | I
Hypercare & incident triage | I | C | C | C | R | C | A | C | I | C | R | C | I
Continuous eval & drift monitoring | I | C | C | C | R | C | C | C | I | I | A | I | I
Benefits realisation tracking | I | A | C | I | I | I | I | I | I | C | I | C | I
Quarterly governance review | A | C | C | C | C | C | C | R | I | I | C | I | R

## Execution Checklist
Execution Checklist — Phase-by-phase
Tick items per phase before progressing. Designed as a working go/no-go list.
|  |  | % Complete: | 0%
Phase | # | Checklist item | Owner role | Done? (Y/N)
1. Discovery | 1 | Executive sponsor named & engaged | Project Manager | N
1. Discovery | 2 | Use cases scored on value × feasibility × risk × data readiness | Product Owner | N
1. Discovery | 3 | Agent vs. simple-automation triage completed | Solution Architect | N
1. Discovery | 4 | Quantified business case with leading + lagging KPIs | Product Owner | N
1. Discovery | 5 | Use-case charter signed off (Gate G1) | Sponsor | N
2. Design | 6 | Agent pattern chosen (single / orchestrator / multi-agent) with rationale | Solution Architect | N
2. Design | 7 | Model selection matrix completed (capability, cost, latency, hosting, residency) | AI/ML Engineer | N
2. Design | 8 | Tool & MCP inventory (with build/buy decision per tool) | Solution Architect | N
2. Design | 9 | Memory + RAG approach documented | AI/ML Engineer | N
2. Design | 10 | Guardrails, PII handling, tool allow-lists, HITL points defined | Security & Risk | N
2. Design | 11 | Reference architecture approved by ARB (Gate G2) | ARB chair | N
3. Data & Infra | 12 | Data inventory + lineage captured for all sources | Data Engineer | N
3. Data & Infra | 13 | Data sharing / DPA agreements signed | Legal / Compliance | N
3. Data & Infra | 14 | KB & vector store built and retrieval-quality baselined | AI/ML Engineer | N
3. Data & Infra | 15 | Dev / Test / Prod environments with IAM and cost guardrails | MLOps / Platform | N
3. Data & Infra | 16 | Observability: trace, prompt log, token / cost dashboards live | MLOps / Platform | N
3. Data & Infra | 17 | Readiness gate passed (Gate G3) | Solution Architect | N
4. Build | 18 | Prompt library versioned in source control | AI/ML Engineer | N
4. Build | 19 | All required tools / MCP servers wired with schemas & error handling | AI/ML Engineer | N
4. Build | 20 | Orchestration loop with max-turn guard, retries, and HITL hooks | AI/ML Engineer | N
4. Build | 21 | Front-end / channel integrated; auth + entitlements working | AI/ML Engineer | N
4. Build | 22 | Automated eval harness wired to CI | QA / Eval Lead | N
4. Build | 23 | MVP demo + code review complete (Gate G4) | Project Manager | N
5. Test & Eval | 24 | Functional eval ≥ target accuracy / quality threshold | QA / Eval Lead | N
5. Test & Eval | 25 | Red-team: prompt injection, jailbreak, data exfil, tool misuse scenarios | Security & Risk | N
5. Test & Eval | 26 | Human review on stratified sample (≥ 100 outputs) | QA / Eval Lead | N
5. Test & Eval | 27 | Latency and per-request cost within SLA | AI/ML Engineer | N
5. Test & Eval | 28 | Quality & safety gate passed (Gate G5) | Security & Risk + QA Lead | N
6. Pilot / UAT | 29 | Pilot cohort selected, trained, baseline KPIs captured | Business SME | N
6. Pilot / UAT | 30 | Daily issue triage + weekly prompt/policy iteration cadence running | Product Owner | N
6. Pilot / UAT | 31 | UAT scenarios executed & signed off | Business SME | N
6. Pilot / UAT | 32 | Go / No-Go decision recorded (Gate G6) | Sponsor | N
7. Deploy & Change | 33 | Cutover runbook + rollback plan reviewed | MLOps / Platform | N
7. Deploy & Change | 34 | Role-based training delivered to all user groups | Change & Adoption | N
7. Deploy & Change | 35 | Launch comms, FAQ and support channel live | Change & Adoption | N
7. Deploy & Change | 36 | Production go-live + hypercare team active (Gate G7) | Project Manager | N
8. Monitor & Scale | 37 | Hypercare incidents triaged; no open Sev-1 | MLOps / Platform | N
8. Monitor & Scale | 38 | Continuous eval running on every release; drift watched | QA / Eval Lead | N
8. Monitor & Scale | 39 | Cost / performance optimisation review done | AI/ML Engineer | N
8. Monitor & Scale | 40 | Benefits realisation tracker updated monthly | Product Owner | N
8. Monitor & Scale | 41 | Quarterly AI governance review held (Gate G8) | Security & Risk | N
8. Monitor & Scale | 42 | Next use case scoped using the same platform | Product Owner | N

## Risk Register
Risk Register
Probability (1-5) × Impact (1-5) = Score. Score auto-calculated; colour-coded heat.
ID | Risk | Category | Probability (1-5) | Impact (1-5) | Score | Mitigation | Owner | Status
R01 | Hallucinated outputs reach end users | Quality / Safety | 4 | 5 | 20 | Strict eval gates, RAG with citations, HITL on high-stakes actions, confidence thresholds | QA / Eval Lead | Open
R02 | Prompt injection or tool misuse via untrusted content | Security | 4 | 5 | 20 | Input sanitisation, tool allow-lists, sandboxed execution, red-team in every release | Security & Risk | Open
R03 | PII / sensitive data leakage through prompts or logs | Privacy | 3 | 5 | 15 | Pre-prompt redaction, log scrubbing, minimum necessary data, DLP rules | Security & Risk | Open
R04 | Runaway token / API costs from agent loops | Cost / Operations | 4 | 4 | 16 | Max-turn guards, budget alerts, model routing, cache, regular cost reviews | MLOps / Platform | Open
R05 | Latency exceeds SLA; user adoption drops | Performance | 3 | 4 | 12 | Parallel tool calls, response streaming, smaller models for triage, async patterns | AI/ML Engineer | Open
R06 | Knowledge base quality / staleness degrades answers | Data | 4 | 4 | 16 | Owners per source, refresh SLAs, retrieval-quality monitoring, content QA | Data Engineer | Open
R07 | Regulatory / compliance violation (EU AI Act, sector rules) | Compliance | 3 | 5 | 15 | Risk-tier classification, documentation, model cards, audit logs, legal review at G2 & G6 | Legal / Compliance | Open
R08 | Low business adoption post go-live | Change | 3 | 4 | 12 | Role-based training, super-user network, embed in existing workflow, exec endorsement | Change & Adoption | Open
R09 | Model deprecation / vendor change disrupts service | Vendor | 3 | 3 | 9 | Abstraction layer, model-agnostic prompts, dual-model contingency, vendor SLAs | Solution Architect | Open
R10 | Drift in eval scores after prompts / data changes | Quality | 4 | 3 | 12 | Automated eval on every PR, canary releases, rollback procedure, alerting on drift | QA / Eval Lead | Open
R11 | Unclear accountability when agent action causes harm | Governance | 2 | 5 | 10 | Documented HITL boundaries, decision rights, audit trail, escalation path | Sponsor | Open
R12 | Scope creep & shifting use case during build | Delivery | 4 | 3 | 12 | Locked charter at G1, formal change control, prioritise backlog ruthlessly | Project Manager | Open

## Status Report
Weekly Status Report — Template
Duplicate the sheet (or copy the block) weekly. Fill RAG via the dropdown.
Reporting period
Reported by
Overall status | Green
Schedule status | Green
Cost status | Green
Quality / safety status | Green
Risk status | Amber
Scope status | Green
1. Headlines (what the steerco must know in 60 seconds)
# | Headline | So-what
1 | e.g. Pilot week 2: agent resolved 68% of tier-1 tickets unaided | On track to hit 70% target before G6
2. Progress this week
Workstream | What we did | % complete | On schedule?
Build | Tools 3 & 4 wired; orchestration loop refactored | 60% | Yes
3. Plans for next week
Workstream | What we will do | Owner | Due
Eval | Run full eval harness on v0.4 | QA Lead | Fri
4. Issues, blockers & decisions needed
# | Issue / decision | Owner | Needed by | Status | Notes
1 | Confirm production VPC peering with security | MLOps | EOW | Open
5. Top risks (top 3 by score from Risk Register)
ID | Risk | Score | Mitigation status
R02 | Prompt injection / tool misuse | 20 | Red-team week 17
6. KPIs (from value case)
KPI | Target | Latest | Trend | Comment
First-pass resolution rate | ≥ 70% | 62% | ↑ | Tracking; eval improving
Cost per request | ≤ $0.05 | $0.07 | → | Cache tuning in flight
Avg latency (p95) | ≤ 6s | 7.2s | ↓ | Parallel tool calls landing wk 17

## Decision Log
Decision Log — Template
Capture every directional decision. Decisions reduce future debate and create an audit trail.
Decision ID | Date | Phase | Decision | Rationale & alternatives considered | Decision-maker | Impacted areas | Status
D001 | yyyy-mm-dd | 2. Design | Adopt orchestrator-with-sub-agents pattern over single agent | Use case requires parallel research + drafting; single agent context-window risk | Solution Architect | Architecture, Build | Approved
D002 | yyyy-mm-dd | 2. Design | Primary model: Claude Sonnet; fallback: smaller routing model | Quality, tool use, cost balance; abstraction layer enables future switch | Solution Architect | Build, Cost | Approved
D003 | yyyy-mm-dd | 5. Test & Eval | Quality gate threshold = 85% on golden eval set + 0 Sev-1 safety findings | Aligned to user-perceivable quality bar; conservative for first release | Sponsor | Test, Pilot | Approved