## Slide 1
PMO PLAYBOOK
Agentic Offering
Project plan, RACI, checklist & execution templates
8
Phases · Discovery to Scale
8
Stage gates · No gate, no spend
24+
Weeks first cycle · re-usable platform
Prepared by the Project Management Office · Working pack for engagement leads

## Slide 2
INSIDE THIS PACK
What we'll cover
01
Why agentic, why a structured plan
Context & operating model
02
The 8-phase roadmap
End-to-end view, week by week
03
Phase deep-dives (4 × 2 phases)
Activities, owners, deliverables
04
Governance & RACI
Who does what, who decides
05
Top risks & mitigations
Where agentic projects fail, and how we don't
06
Success metrics & KPIs
How we'll know it worked
07
Execution checklist & next steps
Working artifacts in the Excel pack
Agentic Offering · Project Plan
2 / 12

## Slide 3
CONTEXT
Why agentic projects need their own playbook
Agents aren't apps
They plan, choose tools, hold memory, and act. Traditional SDLC misses safety, eval and HITL design.
Quality is probabilistic
Outputs vary across runs. We need eval harnesses, not just unit tests, and red-team passes before any gate.
Value compounds across use cases
Platform investments (tools, memory, observability) pay back as we scale to use-case #2 and beyond.
Governance is the throughput limiter
Security, legal, data and risk must be on the team from day 1 — not gate-keepers at the end.
OPERATING PRINCIPLES
One sponsor, one product owner, one architect — no shared accountability
Stage gates are real. No gate, no spend on the next phase
Eval before users. Red-team before production
Cost & latency are first-class metrics, not after-thoughts
Human-in-the-loop on every high-stakes action until trust is earned
Build the platform once. Scale to many use cases
Agentic Offering · Project Plan
3 / 12

## Slide 4
END-TO-END VIEW
The 8-phase roadmap
P1 · Discovery
W1–W3
P2 · Design
W4–W6
P3 · Data & Infra
W7–W10
P4 · Build
W11–W15
P5 · Test & Red-Team
W16–W18
P6 · Pilot / UAT
W19–W21
P7 · Deploy
W22–W23
P8 · Monitor & Scale
W24+
P1
Discovery
W1–W3
P2
Design
W4–W6
P3
Data & Infra
W7–W10
P4
Build
W11–W15
P5
Test & Red-Team
W16–W18
P6
Pilot / UAT
W19–W21
P7
Deploy
W22–W23
P8
Monitor & Scale
W24+
Agentic Offering · Project Plan
4 / 12

## Slide 5
PHASE DEEP-DIVES · 1 OF 4
Discovery & Design
PHASE 1
Discovery & Use-Case Definition
Weeks 1–3
Outcome: Prioritised use case + value case + signed charter
Key activities
Sponsor & stakeholder alignment
Use-case long-list & prioritisation (value × feasibility × risk × data)
Agent vs. simple-automation triage
Value case with leading + lagging KPIs
Deliverables
Use-case charter
Scored backlog
KPI tree
Exit gate:
G1 · Use-case charter signed-off
PHASE 2
Strategy, Architecture & Design
Weeks 4–6
Outcome: Approved target architecture and tech stack
Key activities
Agent pattern: single, orchestrator, or multi-agent
Model selection (capability, latency, cost, residency)
Tools, MCP and integrations map
Memory + RAG design
Guardrails, safety, HITL points
Deliverables
Solution architecture doc
Model & tool matrix
Guardrail policy
Exit gate:
G2 · Architecture Review Board approval
Agentic Offering · Project Plan
5 / 12

## Slide 6
PHASE DEEP-DIVES · 2 OF 4
Data, Infrastructure & Build
PHASE 3
Data Readiness & Infra Setup
Weeks 7–10
Outcome: Data, KB and environments production-ready
Key activities
Data inventory, lineage & access (DPAs signed)
Knowledge base + vector store with retrieval baseline
Dev / Test / Prod environments with IAM & cost guardrails
Observability: tracing, prompt log, token & cost metrics
Deliverables
Data inventory
Production KB
Observability dashboard
Exit gate:
G3 · Data & infra readiness review
PHASE 4
Build & Develop Agent
Weeks 11–15
Outcome: Working MVP agent in dev, demoable end-to-end
Key activities
Versioned prompt & policy library
Tool development & MCP wiring with error handling
Orchestration loop, sub-agents, retries, HITL hooks
Front-end / channel integration
Automated eval harness wired to CI
Deliverables
MVP agent
Tool library
Eval harness
Exit gate:
G4 · MVP demo + code review
Agentic Offering · Project Plan
6 / 12

## Slide 7
PHASE DEEP-DIVES · 3 OF 4
Test, Eval, Pilot & UAT
PHASE 5
Test, Eval & Red-Team
Weeks 16–18
Outcome: Eval scorecard meets thresholds; no Sev-1 safety findings
Key activities
Functional & regression eval on full dataset
Adversarial red-team (prompt injection, jailbreak, exfil, tool misuse)
Human review on stratified sample of outputs
Performance & cost tuning to hit SLAs
Deliverables
Eval scorecard
Red-team report
Tuned MVP
Exit gate:
G5 · Quality & safety gate
PHASE 6
Pilot / UAT
Weeks 19–21
Outcome: Business sign-off and clear Go / No-Go for production
Key activities
Pilot cohort onboarding (10–30 users)
Daily issue triage; weekly prompt/policy iteration
Structured UAT against acceptance criteria
Steerco Go / No-Go decision
Deliverables
Pilot results
UAT sign-off
Go / No-Go record
Exit gate:
G6 · Go / No-Go for production
Agentic Offering · Project Plan
7 / 12

## Slide 8
PHASE DEEP-DIVES · 4 OF 4
Deploy, Monitor & Scale
PHASE 7
Deployment & Change Mgmt
Weeks 22–23
Outcome: Live agent, trained users, hypercare active
Key activities
Production cutover plan + rollback runbook
Role-based training & enablement
Launch comms, FAQ, support channel
Phased rollout with hypercare team
Deliverables
Cutover runbook
Training pack
Launch comms
Exit gate:
G7 · Production go-live
PHASE 8
Monitor, Optimise & Scale
Week 24+
Outcome: Steady-state ops, benefits realised, next use case scoped
Key activities
Hypercare & incident triage (first 2–4 weeks)
Continuous eval, drift monitoring
Cost & performance optimisation
Benefits realisation tracking vs business case
Scale platform to the next use case
Deliverables
Drift dashboard
Benefits tracker
Scale-up plan
Exit gate:
G8 · Quarterly AI governance review
Agentic Offering · Project Plan
8 / 12

## Slide 9
GOVERNANCE
Who does what · RACI snapshot
R
Responsible · does the work
A
Accountable · single owner
C
Consulted · two-way input
I
Informed · one-way comms
Activity
Sponsor
Prod Owner
PM
Architect
AI Eng
Sec & Risk
QA Lead
Change
Use-case prioritisation
A
R
C
C
C
C
I
I
Architecture & design
I
C
I
A
R
C
C
I
Guardrails & HITL
I
C
C
C
C
A
R
I
KB & data setup
I
C
I
C
R
C
I
I
Agent build & tools
I
C
I
C
A
I
R
I
Eval, red-team & gate
I
C
I
C
C
A
R
I
Pilot, UAT & Go/No-Go
A
R
C
I
C
C
C
C
Production go-live
I
C
R
C
C
C
C
A
Full 26-row RACI is in the Excel pack · 'RACI Matrix' tab
Agentic Offering · Project Plan
9 / 12

## Slide 10
RISK LENS
Where agentic projects fail — and how we don't
20
score
R01 · Hallucinated outputs reach users
Mitigation: Strict eval gates, RAG with citations, HITL on high-stakes actions
20
score
R02 · Prompt injection / tool misuse
Mitigation: Input sanitisation, tool allow-lists, sandboxed exec, red-team per release
15
score
R03 · PII / data leakage via prompts/logs
Mitigation: Pre-prompt redaction, log scrubbing, minimum-necessary data, DLP rules
16
score
R04 · Runaway token / API costs
Mitigation: Max-turn guards, budget alerts, model routing, cache, cost reviews
15
score
R07 · Regulatory / compliance violation
Mitigation: Risk-tier classification, model cards, audit logs, legal review at G2 & G6
12
score
R08 · Low business adoption post go-live
Mitigation: Role-based training, super-user network, embed in workflow, exec endorsement
Full 12-risk register with probability × impact scoring in the Excel pack
Agentic Offering · Project Plan
10 / 12

## Slide 11
SUCCESS
How we'll know it worked
Business outcomes
Hours saved per user / week
≥ 5h
First-pass resolution rate
≥ 70%
Revenue / value uplift
vs business case
NPS from agent users
≥ +30
Quality & safety
Eval score on golden set
≥ 85%
Hallucination rate (sample)
< 2%
Sev-1 safety findings
= 0
HITL override rate
trending ↓
Performance & cost
p95 latency
≤ 6s
Cost per successful request
≤ target
Token efficiency
↓ MoM
Availability
≥ 99.5%
Adoption & scale
Weekly active users
↑ each month
Use cases live on platform
≥ 3 by month 12
Time-to-onboard next case
≤ 8 weeks
Tool / prompt re-use
≥ 60%
Agentic Offering · Project Plan
11 / 12

## Slide 12
MAKE IT REAL
Execution checklist & next steps
Execution checklist (highlights from Excel pack)
Sponsor named · charter signed · KPIs defined
Architecture approved by ARB
Data inventory + DPAs + observability live
Prompt library versioned · eval harness in CI
Red-team passed · no Sev-1 findings
Pilot KPIs met · business UAT signed
Cutover runbook + rollback + training
Hypercare active · benefits tracker live
NEXT 30 DAYS
1
Confirm sponsor + product owner
Lock single accountability before any other commitment
2
Run use-case workshop
Score 6–10 candidates; pick 1 for first cycle
3
Stand up the core team
Architect, AI engineer, data engineer, sec & risk, eval lead
4
Schedule G1 gate review
Charter sign-off in week 3
Excel pack: Project Plan · RACI · Checklist · Risks · Status & Decision templates
Agentic Offering · Project Plan
12 / 12